## Change Request Log Template
Change Request Log Template
Request No. | Change ID | Submitted By | Date Submitted | Project Name | Program Manager Name | Change Request Type | Date Identified | Description | Status | Priority | Assigned | Expected Resolution | Action | Impact | Date Work Begins | Escalation Required | Resolution Date | Signoff | Comments
1 | CR-01 | Jane Smith | 2023-01-05 | Project Alpha | A. Clarke | Technical | 2023-01-04 | Server upgrade needed | Closed | High | T. Doe | 2023-01-15 | Review | Schedule | 2023-01-06 | No | 2023-01-16 | A. Clarke | -
2 | CR-02 | John Doe | 2023-07-23 | Project Alpha | A. Clarke | Regulatory/Compliance | 2023-07-23 | Compliance Irregularities | In-Progress | Medium | P.Roe | 2023-08-21 | Documentation | Schedule | 2023-07-24 | No

## Column Headers Explanation
Change Request Log Template
Request No. | Change ID | Submitted By | Date Submitted | Project Name | Program Manager Name | Change Request Type | Date Identified | Description | Status | Priority | Assigned | Expected Resolution | Action | Impact | Date Work Begins | Escalation Required | Resolution Date | Signoff | Comments
A unique, sequential identifier for each change request, which aids in keeping track and referencing. | Unique identifier, often a more formal or structured code, for the change request that might tie into other documentation or systems. | The name or designation of the individual or team who identified the need for change and initiated the request. | The exact date on which the change request was formally submitted. | The specific name of the project that the change request pertains to. | The name of the individual overseeing the program, especially if multiple projects fall under a larger program. | The category or nature of the change, such as technical, functional, scope, etc. | The date when the potential need for change was first observed or identified. | A brief narrative explaining the change, its nature, and its context. | Indicates where the change request is in its lifecycle | The urgency or importance of the change, categorized as high, medium, low, etc., often based on its impact and criticality. | The person or team responsible for investigating, validating, and executing the change request. | The anticipated date by which the change request will be resolved or implemented. | The specific steps or tasks required to implement the change or address the request. | What will be impacted | The date when the actual work or tasks to implement the change starts. | A binary (Yes/No) indicator that determines if higher management intervention or additional resources are needed for the change request. | The actual date when the change request was successfully implemented and closed. | An acknowledgment by the responsible authority, usually a project or program manager, that the change request was executed satisfactorily. | Space for any additional notes, context, or feedback that doesn't fit under the other headers but is relevant to the change request.