## Detailed Change Roadmap
Get Your Free Change Management Software
AI Change Communication Strategy - Change Implementation Plan | [5 empty] | 2025-07-29 |  |  | 1 |  |  |  |  | 2 |  |  |  |  | 3 |  |  |  |  | 4 |  |  |  |  | 5 |  |  |  |  | 6 |  |  |  |  | 7 |  |  |  |  | 8 |  |  |  |  | 9 |  |  |  |  | 10 |  |  |  |  | 11 |  |  |  |  | 12 |  |  |  |  | 13 |  |  |  |  | 14 |  |  |  |  | 15 |  |  |  |  | 16 |  |  |  |  | 17 |  |  |  |  | 18 |  |  |  |  | 19 |  |  |  |  | 20 |  |  |  |  | 21 |  |  |  |  | 22 |  |  |  |  | 23 |  |  |  |  | 24 |  |  |  |  | 25 |  |  |  |  | 26 |  |  |  |  | 27 |  |  |  |  | 28 |  |  |  |  | 29 |  |  |  |  | 30 |  |  |  |  | 31 |  |  |  |  | 32 |  |  |  |  | 33 |  |  |  |  | 34 |  |  |  |  | 35 |  |  |  |  | 36 |  |  |  |  | 37 |  |  |  |  | 38 |  |  |  |  | 39 |  |  |  |  | 40 |  |  |  |  | 41 |  |  |  |  | 42 |  |  |  |  | 43 |  |  |  |  | 44 |  |  |  |  | 45 |  |  |  |  | 46 |  |  |  |  | 47 |  |  |  |  | 48 |  |  |  |  | 49 |  |  |  |  | 50 |  |  |  |  | 51 |  |  |  |  | 52 |  |  |  |  | 53 |  |  |  |  | 54 |  |  |  |  | 55 |  |  |  |  | 56 |  |  |  |  | 57 |  |  |  |  | 58 |  |  |  |  | 59 |  |  |  |  | 60 |  |  |  |  | 61 |  |  |  |  | 62 |  |  |  |  | 63 |  |  |  |  | 64 |  |  |  |  | 65 |  |  |  |  | 66 |  |  |  |  | 67 | [70 empty] | 2025-07-28
# | Phase | What | Details | Start Date | Due Date | Status | Details / Adminstrative Notes | - | 2025-07-28 | 2025-07-29 | 2025-07-30 | 2025-07-31 | 2025-08-01 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-09-01 | 2025-09-02 | 2025-09-03 | 2025-09-04 | 2025-09-05 | 2025-09-08 | 2025-09-09 | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-15 | 2025-09-16 | 2025-09-17 | 2025-09-18 | 2025-09-19 | 2025-09-22 | 2025-09-23 | 2025-09-24 | 2025-09-25 | 2025-09-26 | 2025-09-29 | 2025-09-30 | 2025-10-01 | 2025-10-02 | 2025-10-03 | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-09 | 2025-10-10 | 2025-10-13 | 2025-10-14 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 2025-10-20 | 2025-10-21 | 2025-10-22 | 2025-10-23 | 2025-10-24 | 2025-10-27 | 2025-10-28 | 2025-10-29 | 2025-10-30 | 2025-10-31 | 2025-11-03 | 2025-11-04 | 2025-11-05 | 2025-11-06 | 2025-11-07 | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-17 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 2025-11-21 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28 | 2025-12-01 | 2025-12-02 | 2025-12-03 | 2025-12-04 | 2025-12-05 | 2025-12-08 | 2025-12-09 | 2025-12-10 | 2025-12-11 | 2025-12-12 | 2025-12-15 | 2025-12-16 | 2025-12-17 | 2025-12-18 | 2025-12-19 | 2025-12-22 | 2025-12-23 | 2025-12-24 | 2025-12-25 | 2025-12-26 | 2025-12-29 | 2025-12-30 | 2025-12-31 | 2026-01-01 | 2026-01-02 | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 | 2026-05-01 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-15 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-19 | 2026-06-22 | 2026-06-23 | 2026-06-24 | 2026-06-25 | 2026-06-26 | 2026-06-29 | 2026-06-30 | 2026-07-01 | 2026-07-02 | 2026-07-03 | 2026-07-06 | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-03 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-07 | 2026-08-10 | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-17 | 2026-08-18 | 2026-08-19 | 2026-08-20 | 2026-08-21 | 2026-08-24 | 2026-08-25 | 2026-08-26 | 2026-08-27 | 2026-08-28 | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-03 | 2026-09-04 | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06 | 2026-11-09 | 2026-11-10 | 2026-11-11 | 2026-11-12 | 2026-11-13 | 2026-11-16 | 2026-11-17 | 2026-11-18 | 2026-11-19 | 2026-11-20 | 2026-11-23 | 2026-11-24 | 2026-11-25 | 2026-11-26 | 2026-11-27 | 2026-11-30 | 2026-12-01 | 2026-12-02 | 2026-12-03 | 2026-12-04 | 2026-12-07 | 2026-12-08 | 2026-12-09 | 2026-12-10 | 2026-12-11 | 2026-12-14 | 2026-12-15 | 2026-12-16 | 2026-12-17 | 2026-12-18 | 2026-12-21 | 2026-12-22 | 2026-12-23 | 2026-12-24 | 2026-12-25 | 2026-12-28 | 2026-12-29 | 2026-12-30 | 2026-12-31 | 2027-01-01 | 2027-01-04 | 2027-01-05 | 2027-01-06 | 2027-01-07 | 2027-01-08 | 2027-01-11 | 2027-01-12 | 2027-01-13 | 2027-01-14 | 2027-01-15 | 2027-01-18 | 2027-01-19 | 2027-01-20 | 2027-01-21 | 2027-01-22 | 2027-01-25 | 2027-01-26 | 2027-01-27 | 2027-01-28 | 2027-01-29 | 2027-02-01 | 2027-02-02 | 2027-02-03 | 2027-02-04 | Start Date | Due Date
1 | Assess | 6-12 Weeks Roadmap | Finalize this 6-12 weeks roadmap | 2025-07-29 | 2025-08-06 | In-Progress | [401 empty] | 2025-07-29 | 2025-08-06
2 | Assess | Introductions | Send Change Manager intro email to project team and key stakeholders | 2025-08-01 | 2025-08-08 | Pending | [401 empty] | 2025-08-01 | 2025-08-08
3 | Assess | Key Stakeholder Meetings | Conduct 1-on-1 virtual or in-person meet and greet meetings with PMs, sponsors, and key stakeholders | 2025-08-01 | 2025-08-15 | Pending | [401 empty] | 2025-08-01 | 2025-08-15
4 | Assess | Project Understanding | Understand the project scope, timeline, deliverables, objectives, success indicators, and milestones. | 2025-08-01 | 2025-08-15 | Pending | [401 empty] | 2025-08-01 | 2025-08-15
5 | Assess | Project Risk Assessment | Identify the project risk and level of change management needed. | 2025-08-01 | 2025-08-13 | Pending | [401 empty] | 2025-08-01 | 2025-08-13
6 | Assess | Sponsor Assessment | Assess project sponsors to determine level of availability, enthusiasm, and risk level. | 2025-08-01 | 2025-08-13 | Pending | [401 empty] | 2025-08-01 | 2025-08-13
7 | Assess | Stakeholder Assessment | Assess stakeholder to determine level of support, influence, and capacity | 2025-08-01 | 2025-08-22 | Pending | [401 empty] | 2025-08-01 | 2025-08-22
8 | Assess | Change Impact Assessment | Assess change impacts to determine each audience's level of impact. | 2025-08-01 | 2025-08-28 | Pending | [401 empty] | 2025-08-01 | 2025-08-28
9 | Assess | Readiness Assessment | Conduct org readiness assessment to identify awareness, acceptance of the change, knowledge, proficiency, and readiness for the change | 2025-08-06 | 2025-08-27 | Pending | [401 empty] | 2025-08-06 | 2025-08-27
10 | Assess | Communication Assessments | Determine communications needed to engage with impacted audiences. Draft, socialize and send any initial awareness communications. | 2025-08-07 | 2025-08-28 | Pending | [401 empty] | 2025-08-07 | 2025-08-28
11 | Assess | Resistance Level Assessments | Assess where resistance currently exists and also where it might arise from in the future. | 2025-08-07 | 2025-08-28 | Pending | [401 empty] | 2025-08-07 | 2025-08-28
12 | Assess | Status Updates | Provide status updates and conduct regular touchpoints with project/program leads, sponsors and stakeholders | Ongoing | Ongoing | Pending | [10 empty] | X |  |  |  |  | X |  |  |  |  | X |  |  |  |  | X |  |  |  |  | X | [370 empty] | Ongoing | Ongoing
13 | Develop | Change Management Playbook | Develop Change Management Strategic Playbook | 2025-08-21 | 2025-09-11 | Pending | [401 empty] | 2025-08-21 | 2025-09-11
14 | Develop | Change Management Plans | Develop Change Management Plans (Comms, engagement/briefings, training, change champions, and more) | 2025-08-28 | 2025-09-18 | Pending | [401 empty] | 2025-08-28 | 2025-09-18
15 | Develop | Strategic Playbook & Change Plans Finalization | Socialize Strategic Playbook and Plans, integrate feedback, and finalize | 2025-09-02 | 2025-09-23 | Pending | [401 empty] | 2025-09-02 | 2025-09-23
16 | Develop | Develop AI Communication Plan | Create the AI Communication Plan. | [404 empty] | 0 | 0
17 | Develop | Develop AI Communication Plan | Identify a complete target list of internal or/and external communication audience groups. | [404 empty] | 0 | 0
18 | Develop | Develop AI Communication Plan | Determine the key communication objectives and messages. | [404 empty] | 0 | 0
19 | Develop | Develop AI Communication Plan | Develop/identify communication assets (templates, core images, key messages, delivery tools/applications. | [404 empty] | 0 | 0
20 | Develop | Develop AI Stakeholder Plan | Create the Stakeholder Engagement Plan. | [404 empty] | 0 | 0
21 | Develop | Develop AI Stakeholder Plan | Develop customized presentation materials for engaging with stakeholders. | [404 empty] | 0 | 0
22 | Develop | Develop AI Sponsor Plan | Develop a plan for engaging and supporting project sponsors. | [404 empty] | 0 | 0
23 | Develop | Resistance Management Plan | Create the resistance management plan. | [404 empty] | 0 | 0
24 | Develop | Change Champions / Agents Plan | Create the Change Champions / Agents Plan (if needed) | [404 empty] | 0 | 0
25 | Develop | Change Champions / Agents Network Assets | Develop customized materials for enabling the Change Champions/Agents Network. | [404 empty] | 0 | 0
26 | Develop | Develop Training Plan | Create the training plan (if training is needed). | [404 empty] | 0 | 0
27 | Develop | Develop Training Plan | Compile the complete list of Trainees & enter into a training tracking tool. | [404 empty] | 0 | 0
28 | Develop | Develop Training Plan | Develop the training program & training assets. | [404 empty] | 0 | 0
29 | Develop | Coaching Plan | Create the Coaching Plan (if needed) | [404 empty] | 0 | 0
30 | Develop | Develop Post Go-Live Support Plan | Create the Change Adoption Reinforcement Plan. | [404 empty] | 0 | 0
31 | Deploy | Assess & Track Change Risk | Continue checking off Stage 2 project deliverables. | [404 empty] | 0 | 0
32 | Deploy | Deploy Communications Plan | Execute the communications plan. | [404 empty] | 0 | 0
33 | Deploy | Deliver Communications | Send awareness and "what's next" communications to impacted groups. | [404 empty] | 0 | 0
34 | Deploy | Deliver Communications | Send out surveys and questionnaires to measure how aware employees are of the change and how much desire and support they have for the change. | [404 empty] | 0 | 0
35 | Deploy | Deliver Communications | Send training, logistics, and training reminder communications to impacted groups. | [404 empty] | 0 | 0
36 | Deploy | Deliver Communications | Send progress update communications to keep impacted groups and stakeholders informed. | [404 empty] | 0 | 0
37 | Deploy | Deliver Communications | Send "Get Ready" communications. | [404 empty] | 0 | 0
38 | Deploy | Deliver Communications | Send Go-Live communication with details on where to find support after the go-live date | [404 empty] | 0 | 0
39 | Deploy | Deliver Org Readiness | Conduct the additional readiness surveys, review the results, and plan stakeholder engagement. | [404 empty] | 0 | 0
40 | Deploy | Deploy Change Champions | Launch the change network & conduct a Kick-Off Meeting | [404 empty] | 0 | 0
41 | Deploy | Deploy Change Champions | Conduct ongoing touch-base meetings with the Change Champions/Agents Network. | [404 empty] | 0 | 0
42 | Deploy | Engage & Manage Stakeholders | Implement the stakeholder engagement plan. | [404 empty] | 0 | 0
43 | Deploy | Engage & Manage Stakeholders | Track and manage stakeholder engagement. | [404 empty] | 0 | 0
44 | Deploy | Engage & Manage Sponsors | Schedule regular touch-base/update sessions with project sponsors. | [404 empty] | 0 | 0
45 | Deploy | Engage & Manage Sponsors | Support and engage sponsors and leaders. | [404 empty] | 0 | 0
46 | Deploy | Mitigate Resistance to Change | Deploy the resistance management plan. | [404 empty] | 0 | 0
47 | Deploy | Mitigate Resistance to Change | Conduct ongoing meetings to track resistance mitigation & identify new resistance. | [404 empty] | 0 | 0
48 | Deploy | Deliver & Track Training | Deliver the training program. | [404 empty] | 0 | 0
49 | Deploy | Deliver & Track Training | Survey trainees to measure the effectiveness and success of the training program. | [404 empty] | 0 | 0
50 | Deploy | Deliver & Track Training | Follow-up with trained employees, and provide additional training as needed. | [404 empty] | 0 | 0
51 | Deploy | Deliver Coaching | Schedule coaching sessions with those being coached. | [404 empty] | 0 | 0
52 | Deploy | Deliver Coaching | Deploy Coaching Plan with the individuals being coached. | [404 empty] | 0 | 0
53 | Deploy | Deliver Coaching | Track coaching success and add more sessions if needed. | [404 empty] | 0 | 0
54 | Deploy | Track Pre-Go-Live Adoption KPIs | Survey impacted groups for adoption metrics before the project goes live. | [404 empty] | 0 | 0
55 | Normalize | Assess & Track Change Risk | Review & begin checking off Stage 3 project deliverables. | [265 empty] | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A
56 | Normalize | Normalize New Behaviors | Deploy support & help resources.
57 | Normalize | Normalize New Behaviors | Send out post go-live communications to communicate where to find support resources, project successes, and lessons learned.
58 | Normalize | Follow-up with Users | Survey impacted groups for adoption metrics after the project goes live.
59 | Normalize | Track Adoption Success | Track and address adoption roadblocks.
60 | Normalize | Address New Resistance | Watch for and address any new post-go-live resistance.
61 | Normalize | Reward Change Network | Celebrate successes, thank and reward the Change Champions Network members.
62 | Exit | Assess & Track Change Risk | Continue checking off Stage 3 project deliverables
63 | Exit | Create OCM Exit Plan | Develop a Change Management Transition/Exit Plan
64 | Exit | Transition OCM | Implement the OCM Exit Plan.
65 | Exit | Final Change Project Reports | Draft the final OCM Project Report, including successes & lessons learned.
66 | Exit | Final Change Project Reports | Socialize the draft of the final OCM Project Report with Project Sponsors & the Project Manager and incorporate their input.
67 | Exit | Final Change Project Reports | Finalize, add any additional reports, and disseminate the final OCM Project Report to the relevant parties.
Insert Duplicate Rows
Enter Start Date