## Checklist
Phase | # | Checklist | Owner | Add't Details | Status | Notes
Phase 1: Planning & Preparation | 1 | Define Go-Live Scope & Objectives |  | Clarify success criteria, kpis, and boundaries | Pending
Phase 1: Planning & Preparation | 2 | Develop Comprehensive Go-Live Plan |  | Including cutover strategy, dependencies, risk / contingency plans, and stakeholder communications | Pending
Phase 1: Planning & Preparation | 3 | Establish Clear Timelines & Milestones |  | Align with program roadmap and freeze dates | Pending
Phase 1: Planning & Preparation | 4 | Identify And Engage Stakeholders |  | Business owners, IT, change management, vendors, and support teams | Pending
Phase 1: Planning & Preparation | 5 | Allocate Resources & Roles |  | Confirm ownership of tasks, escalation paths, and on-call coverage | Pending
Phase 1: Planning & Preparation | 6 | Conduct Risk Assessment & Mitigation Planning |  | Define rollback/contingency scenarios | Pending
Phase 1: Planning & Preparation | 7 | Secure & Adapt Go-Live Templates |  | For plans, checklists, readiness assessments, comms, and support | Pending
Phase 1: Planning & Preparation | 8 | Complete Go-Live Readiness Assessment |  | Ensure alignment across business, technical, and change domains | Pending
Phase 1: Planning & Preparation | 9 | Requirements Verified |  | Confirm business, functional, and technical requirements are complete | Pending
Phase 1: Planning & Preparation | 10 | Testing Completed |  | System integration testing, uat, regression, security, and performance tests signed off | Pending
Phase 1: Planning & Preparation | 11 | Data Migration Planning |  | Validate migration approach, test migration, confirm reconciliation process | Pending
Phase 1: Planning & Preparation | 12 | Documentation Ready |  | SOPs, training materials, user guides, and release notes finalized | Pending
Phase 1: Planning & Preparation | 13 | Access & Security Confirmed |  | Verify roles, permissions, and compliance with security standards | Pending
Phase 1: Planning & Preparation | 14 | Training Delivered |  | Ensure end users, support teams, and business leads are trained and confident | Pending
Phase 1: Planning & Preparation | 15 | Disaster Recovery & Rollback Plans |  | Validated and tested | Pending
Phase 1: Planning & Preparation | 16 | Communications Plan Developed |  | Pre-launch notices, faqs, go-live announcements, escalation contacts | Pending
Phase 2: Go-Live Readiness & Final Testing | 17 | Complete All Development & Configuration |  | Code freeze and configuration freeze in place | Pending
Phase 2: Go-Live Readiness & Final Testing | 18 | Finalize And Execute System Testing |  | Performance, load, security, and failover testing | Pending
Phase 2: Go-Live Readiness & Final Testing | 19 | Final User Acceptance Testing (UAT) |  | Confirm sign-off from business owners | Pending
Phase 2: Go-Live Readiness & Final Testing | 20 | Data Migration |  | Dry runs & validation | Pending
Phase 2: Go-Live Readiness & Final Testing | 21 | Finalize User & Internal Team Training |  | Ensure training completion and materials distribution | Pending
Phase 2: Go-Live Readiness & Final Testing | 22 | Confirm Infrastructure & Scalability |  | Servers, cloud, networks, and storage validated | Pending
Phase 2: Go-Live Readiness & Final Testing | 23 | Develop & Approve Cutover Plan |  | Step-by-step execution with owners, timings, and rollback triggers | Pending
Phase 2: Go-Live Readiness & Final Testing | 24 | Pre-Go-Live Backup |  | Take final snapshots of systems and databases | Pending
Phase 2: Go-Live Readiness & Final Testing | 25 | Hypercare Support Team Mobilized |  | Helpdesk, smes, and escalation protocols ready | Pending
Phase 2: Go-Live Readiness & Final Testing | 26 | Final Go-Live Readiness Review |  | Checklist signed off by program, project, and change managers | Pending
Phase 3: Execution (Go-Live Event) | 27 | Final Go-Live Meeting |  | Confirm readiness, issue log clear, and go/no-go decision | Pending
Phase 3: Execution (Go-Live Event) | 28 | Execute Cutover Plan |  | Follow checklist, document steps, track timing | Pending
Phase 3: Execution (Go-Live Event) | 29 | Perform Final System Health Checks |  | Validate integrations, data flows, and reporting | Pending
Phase 3: Execution (Go-Live Event) | 30 | Validate Access & Permissions |  | Confirm all users can log in and perform roles | Pending
Phase 3: Execution (Go-Live Event) | 31 | Send Go-Live Communications |  | Emails, portals, or announcements confirming system availability | Pending
Phase 3: Execution (Go-Live Event) | 32 | Monitor System Performance In Real Time |  | Dashboards, logs, and performance tools | Pending
Phase 3: Execution (Go-Live Event) | 33 | Provide Immediate Support |  | Triage desk and hypercare teams active | Pending
Phase 3: Execution (Go-Live Event) | 34 | Log Issues In Real Time |  | Maintain central issue tracker for transparency | Pending
Phase 4: Post-Launch & Support | 35 | Activate Go-Live Support Plan |  | Hypercare period with extended monitoring and dedicated staffing | Pending
Phase 4: Post-Launch & Support | 36 | Track And Resolve Issues |  | Triage defects, prioritize fixes, escalate blockers | Pending
Phase 4: Post-Launch & Support | 37 | Continuous System Monitoring |  | Uptime, latency, performance, and error logs | Pending
Phase 4: Post-Launch & Support | 38 | Gather User Feedback |  | Surveys, workshops, or town halls | Pending
Phase 4: Post-Launch & Support | 39 | Knowledge Transfer & Documentation |  | Update sops, support docs, and internal knowledge base | Pending
Phase 4: Post-Launch & Support | 40 | Review Lessons Learned |  | Conduct retrospective, document successes, gaps, and recommendations | Pending
Phase 4: Post-Launch & Support | 41 | Plan For Ongoing Enhancements |  | Schedule backlog grooming, continuous improvements | Pending
Phase 4: Post-Launch & Support | 42 | Formal Closure |  | Hold post-go-live review, capture lessons learned, and formally close the project | Pending
Go-Live Checklist for Project, Program & Change Management

## How to Use this Checklist
How to Use this Go-LiveChecklist | https://www.ocmsolution.com/
Walkthrough Guide: How to Use the Go-Live Checklist
This Go-Live Checklist is designed to provide project, program, and change managers with a structured, step-by-step approach to prepare, execute, and support a successful go-live event. It ensures no critical task is missed, and it allows for transparent tracking across teams.
📊 Go-Live Checklist Structure
The checklist is divided into four key phases:
1. Phase 1: Planning & Preparation (Items 1–16)
Focuses on scope, planning, risk, documentation, training, and communications.
Objective: Ensure the foundation for go-live is strong and stakeholders are aligned.
2. Phase 2: Go-Live Readiness & Final Testing (Items 17–26)
Covers final testing, infrastructure readiness, data migration, and cutover planning.
Objective: Validate that the solution and teams are fully prepared for execution.
3. Phase 3: Execution (Go-Live Event) (Items 27–34)
Step-by-step cutover and launch activities.
Objective: Deliver a smooth transition, minimize disruption, and communicate effectively.
4. Phase 4: Post-Launch & Support (Items 35–42)
Includes hypercare, monitoring, feedback, lessons learned, and closure.
Objective: Stabilize operations, capture improvements, and transition to business-as-usual.
📝 How to Use the Checklist
1. Review Each Phase
Begin by familiarizing yourself with tasks under each phase.
Ensure dependencies are identified (e.g., testing must be complete before cutover).
2. Assign Owners
Each task should have a clear owner or responsible team.
You may add an “Owner” column in the Excel sheet to track accountability.
3. Track Status
Use the Status column to update progress.
Status values:
Pending = Not started
In-Progress = Work underway
Completed = Finished
TBD = Pending decision or information
Colors help provide a quick visual snapshot of progress.
4. Monitor Progress By Phase
Filter or group tasks by phase to see readiness at a glance.
Example: Before the Go/No-Go decision, ensure all Phase 1 and Phase 2 items are complete.
5. Use It As A Communication Tool
Share updates with stakeholders regularly (e.g., weekly status updates).
Highlight completed items to show progress and pending ones to show risks.
6. Support Go/No-Go Decisions
Before execution, review the checklist with leadership.
A phase should be at least 90–100% complete before moving to the next.
7. Close The Loop Post-Go-Live
Use Phase 4 to guide hypercare and ensure lessons learned are documented.
Mark the project as “Closed” only when all items in this phase are completed.
🎯 Key Benefits of Using this Go-Live Checklist
Ensures no critical step is missed during go-live.
Provides a single source of truth for tracking readiness.
Promotes accountability by assigning tasks to owners.
Supports clear communication with stakeholders.
Facilitates continuous improvement through lessons learned.
This checklist is a living document – update it regularly, share progress with your teams, and use it to keep the project aligned from planning through post-launch support.