## Detailed Change Roadmap
Detailed Change Implementation Roadmap ¦ E2E | [5 empty] | 2025-11-05 |  |  | 1 |  |  |  |  | 2 |  |  |  |  | 3 |  |  |  |  | 4 |  |  |  |  | 5 |  |  |  |  | 6 |  |  |  |  | 7 |  |  |  |  | 8 |  |  |  |  | 9 |  |  |  |  | 10 |  |  |  |  | 11 |  |  |  |  | 12 |  |  |  |  | 13 |  |  |  |  | 14 |  |  |  |  | 15 |  |  |  |  | 16 |  |  |  |  | 17 |  |  |  |  | 18 |  |  |  |  | 19 |  |  |  |  | 20 |  |  |  |  | 21 |  |  |  |  | 22 |  |  |  |  | 23 |  |  |  |  | 24 |  |  |  |  | 25 |  |  |  |  | 26 |  |  |  |  | 27 |  |  |  |  | 28 |  |  |  |  | 29 |  |  |  |  | 30 |  |  |  |  | 31 |  |  |  |  | 32 |  |  |  |  | 33 |  |  |  |  | 34 |  |  |  |  | 35 |  |  |  |  | 36 |  |  |  |  | 37 |  |  |  |  | 38 |  |  |  |  | 39 |  |  |  |  | 40 |  |  |  |  | 41 |  |  |  |  | 42 |  |  |  |  | 43 |  |  |  |  | 44 |  |  |  |  | 45 |  |  |  |  | 46 |  |  |  |  | 47 |  |  |  |  | 48 |  |  |  |  | 49 |  |  |  |  | 50 |  |  |  |  | 51 |  |  |  |  | 52 |  |  |  |  | 53 |  |  |  |  | 54 |  |  |  |  | 55 |  |  |  |  | 56 |  |  |  |  | 57 |  |  |  |  | 58 |  |  |  |  | 59 |  |  |  |  | 60 |  |  |  |  | 61 |  |  |  |  | 62 |  |  |  |  | 63 |  |  |  |  | 64 |  |  |  |  | 65 |  |  |  |  | 66 |  |  |  |  | 67 | [70 empty] | 2025-11-03
# | Phase | What | Details | Start Date | Due Date | Status | Details / Adminstrative Notes | - | 2025-11-03 | 2025-11-04 | 2025-11-05 | 2025-11-06 | 2025-11-07 | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-17 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 2025-11-21 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28 | 2025-12-01 | 2025-12-02 | 2025-12-03 | 2025-12-04 | 2025-12-05 | 2025-12-08 | 2025-12-09 | 2025-12-10 | 2025-12-11 | 2025-12-12 | 2025-12-15 | 2025-12-16 | 2025-12-17 | 2025-12-18 | 2025-12-19 | 2025-12-22 | 2025-12-23 | 2025-12-24 | 2025-12-25 | 2025-12-26 | 2025-12-29 | 2025-12-30 | 2025-12-31 | 2026-01-01 | 2026-01-02 | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 | 2026-05-01 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-15 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-19 | 2026-06-22 | 2026-06-23 | 2026-06-24 | 2026-06-25 | 2026-06-26 | 2026-06-29 | 2026-06-30 | 2026-07-01 | 2026-07-02 | 2026-07-03 | 2026-07-06 | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-03 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-07 | 2026-08-10 | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-17 | 2026-08-18 | 2026-08-19 | 2026-08-20 | 2026-08-21 | 2026-08-24 | 2026-08-25 | 2026-08-26 | 2026-08-27 | 2026-08-28 | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-03 | 2026-09-04 | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06 | 2026-11-09 | 2026-11-10 | 2026-11-11 | 2026-11-12 | 2026-11-13 | 2026-11-16 | 2026-11-17 | 2026-11-18 | 2026-11-19 | 2026-11-20 | 2026-11-23 | 2026-11-24 | 2026-11-25 | 2026-11-26 | 2026-11-27 | 2026-11-30 | 2026-12-01 | 2026-12-02 | 2026-12-03 | 2026-12-04 | 2026-12-07 | 2026-12-08 | 2026-12-09 | 2026-12-10 | 2026-12-11 | 2026-12-14 | 2026-12-15 | 2026-12-16 | 2026-12-17 | 2026-12-18 | 2026-12-21 | 2026-12-22 | 2026-12-23 | 2026-12-24 | 2026-12-25 | 2026-12-28 | 2026-12-29 | 2026-12-30 | 2026-12-31 | 2027-01-01 | 2027-01-04 | 2027-01-05 | 2027-01-06 | 2027-01-07 | 2027-01-08 | 2027-01-11 | 2027-01-12 | 2027-01-13 | 2027-01-14 | 2027-01-15 | 2027-01-18 | 2027-01-19 | 2027-01-20 | 2027-01-21 | 2027-01-22 | 2027-01-25 | 2027-01-26 | 2027-01-27 | 2027-01-28 | 2027-01-29 | 2027-02-01 | 2027-02-02 | 2027-02-03 | 2027-02-04 | 2027-02-05 | 2027-02-08 | 2027-02-09 | 2027-02-10 | 2027-02-11 | 2027-02-12 | 2027-02-15 | 2027-02-16 | 2027-02-17 | 2027-02-18 | 2027-02-19 | 2027-02-22 | 2027-02-23 | 2027-02-24 | 2027-02-25 | 2027-02-26 | 2027-03-01 | 2027-03-02 | 2027-03-03 | 2027-03-04 | 2027-03-05 | 2027-03-08 | 2027-03-09 | 2027-03-10 | 2027-03-11 | 2027-03-12 | 2027-03-15 | 2027-03-16 | 2027-03-17 | 2027-03-18 | 2027-03-19 | 2027-03-22 | 2027-03-23 | 2027-03-24 | 2027-03-25 | 2027-03-26 | 2027-03-29 | 2027-03-30 | 2027-03-31 | 2027-04-01 | 2027-04-02 | 2027-04-05 | 2027-04-06 | 2027-04-07 | 2027-04-08 | 2027-04-09 | 2027-04-12 | 2027-04-13 | 2027-04-14 | 2027-04-15 | 2027-04-16 | 2027-04-19 | 2027-04-20 | 2027-04-21 | 2027-04-22 | 2027-04-23 | 2027-04-26 | 2027-04-27 | 2027-04-28 | 2027-04-29 | 2027-04-30 | 2027-05-03 | 2027-05-04 | 2027-05-05 | 2027-05-06 | 2027-05-07 | 2027-05-10 | 2027-05-11 | 2027-05-12 | 2027-05-13 | Start Date | Due Date
1 | Assess | 6-Weeks Roadmap | Finalize this 6 weeks roadmap | 2025-11-05 | 2025-11-13 | In-Progress | [401 empty] | 2025-11-05 | 2025-11-13
2 | Assess | Introductions | Send Change Manager intro email to project team and key stakeholders | 2025-11-08 | 2025-11-15 | Pending | [401 empty] | 2025-11-08 | 2025-11-15
3 | Assess | Key Stakeholder Meetings | Conduct 1-on-1 virtual or in-person meet and greet meetings with PMs, sponsors, and key stakeholders | 2025-11-08 | 2025-11-22 | Pending | [401 empty] | 2025-11-08 | 2025-11-22
4 | Assess | Project Understanding | Understand the project scope, timeline, deliverables, objectives, success indicators, and milestones. | 2025-11-08 | 2025-11-22 | Pending | [401 empty] | 2025-11-08 | 2025-11-22
5 | Assess | Project Risk Assessment | Identify the project risk and level of change management needed. | 2025-11-08 | 2025-11-20 | Pending | [401 empty] | 2025-11-08 | 2025-11-20
6 | Assess | Sponsor Assessment | Assess project sponsors to determine level of availability, enthusiasm, and risk level. | 2025-11-08 | 2025-11-20 | Pending | [401 empty] | 2025-11-08 | 2025-11-20
7 | Assess | Stakeholder Assessment | Assess stakeholder to determine level of support, influence, and capacity | 2025-11-08 | 2025-11-29 | Pending | [401 empty] | 2025-11-08 | 2025-11-29
8 | Assess | Change Impact Assessment | Assess change impacts to determine each audience's level of impact. | 2025-11-08 | 2025-12-05 | Pending | [401 empty] | 2025-11-08 | 2025-12-05
9 | Assess | Readiness Assessment | Conduct org readiness assessment to identify awareness, acceptance of the change, knowledge, proficiency, and readiness for the change | 2025-11-13 | 2025-12-04 | Pending | [401 empty] | 2025-11-13 | 2025-12-04
10 | Assess | Communication Assessments | Determine communications needed to engage with impacted audiences. Draft, socialize and send any initial awareness communications. | 2025-11-14 | 2025-12-05 | Pending | [401 empty] | 2025-11-14 | 2025-12-05
11 | Assess | Resistance Level Assessments | Assess where resistance currently exists and also where it might arise from in the future. | 2025-11-14 | 2025-12-05 | Pending | [401 empty] | 2025-11-14 | 2025-12-05
12 | Assess | Status Updates | Provide status updates and conduct regular touchpoints with project/program leads, sponsors and stakeholders | Ongoing | Ongoing | Pending | [10 empty] | X |  |  |  |  | X |  |  |  |  | X |  |  |  |  | X |  |  |  |  | X | [370 empty] | Ongoing | Ongoing
13 | Develop | Change Management Playbook | Develop Change Management Strategic Playbook | 2025-11-28 | 2025-12-19 | Pending | [401 empty] | 2025-11-28 | 2025-12-19
14 | Develop | Change Management Plans | Develop Change Management Plans (Comms, engagement/briefings, training, change champions, and more) | 2025-12-05 | 2025-12-26 | Pending | [401 empty] | 2025-12-05 | 2025-12-26
15 | Develop | Strategic Playbook & Change Plans Finalization | Socialize Strategic Playbook and Plans, integrate feedback, and finalize | 2025-12-10 | 2025-12-31 | Pending | [401 empty] | 2025-12-10 | 2025-12-31
16 | Develop | Develop Communication Plan | Create the Communication Plan. | [404 empty] | 0 | 0
17 | Develop | Develop Communication Plan | Identify a complete target list of internal or/and external communication audience groups. | [404 empty] | 0 | 0
18 | Develop | Develop Communication Plan | Determine the key communication objectives and messages. | [404 empty] | 0 | 0
19 | Develop | Develop Communication Plan | Develop/identify communication assets (templates, core images, key messages, delivery tools/applications. | [404 empty] | 0 | 0
20 | Develop | Develop Stakeholder Plan | Create the Stakeholder Engagement Plan. | [404 empty] | 0 | 0
21 | Develop | Develop Stakeholder Plan | Develop customized presentation materials for engaging with stakeholders. | [404 empty] | 0 | 0
22 | Develop | Develop Sponsor Plan | Develop a plan for engaging and supporting project sponsors. | [404 empty] | 0 | 0
23 | Develop | Resistance Management Plan | Create the resistance management plan. | [404 empty] | 0 | 0
24 | Develop | Change Champions / Agents Plan | Create the Change Champions / Agents Plan (if needed) | [404 empty] | 0 | 0
25 | Develop | Change Champions / Agents Network Assets | Develop customized materials for enabling the Change Champions/Agents Network. | [404 empty] | 0 | 0
26 | Develop | Develop Training Plan | Create the training plan (if training is needed). | [404 empty] | 0 | 0
27 | Develop | Develop Training Plan | Compile the complete list of Trainees & enter into a training tracking tool. | [404 empty] | 0 | 0
28 | Develop | Develop Training Plan | Develop the training program & training assets. | [404 empty] | 0 | 0
29 | Develop | Coaching Plan | Create the Coaching Plan (if needed) | [404 empty] | 0 | 0
30 | Develop | Develop Post Go-Live Support Plan | Create the Change Adoption Reinforcement Plan. | [404 empty] | 0 | 0
31 | Deploy | Assess & Track Change Risk | Continue checking off Stage 2 project deliverables. | [404 empty] | 0 | 0
32 | Deploy | Deploy Communications Plan | Execute the communications plan. | [404 empty] | 0 | 0
33 | Deploy | Deliver Communications | Send awareness and "what's next" communications to impacted groups. | [404 empty] | 0 | 0
34 | Deploy | Deliver Communications | Send out surveys and questionnaires to measure how aware employees are of the change and how much desire and support they have for the change. | [404 empty] | 0 | 0
35 | Deploy | Deliver Communications | Send training, logistics, and training reminder communications to impacted groups. | [404 empty] | 0 | 0
36 | Deploy | Deliver Communications | Send progress update communications to keep impacted groups and stakeholders informed. | [404 empty] | 0 | 0
37 | Deploy | Deliver Communications | Send "Get Ready" communications. | [404 empty] | 0 | 0
38 | Deploy | Deliver Communications | Send Go-Live communication with details on where to find support after the go-live date | [404 empty] | 0 | 0
39 | Deploy | Deliver Org Readiness | Conduct the additional readiness surveys, review the results, and plan stakeholder engagement. | [404 empty] | 0 | 0
40 | Deploy | Deploy Change Champions | Launch the change network & conduct a Kick-Off Meeting | [404 empty] | 0 | 0
41 | Deploy | Deploy Change Champions | Conduct ongoing touch-base meetings with the Change Champions/Agents Network. | [404 empty] | 0 | 0
42 | Deploy | Engage & Manage Stakeholders | Implement the stakeholder engagement plan. | [404 empty] | 0 | 0
43 | Deploy | Engage & Manage Stakeholders | Track and manage stakeholder engagement. | [404 empty] | 0 | 0
44 | Deploy | Engage & Manage Sponsors | Schedule regular touch-base/update sessions with project sponsors. | [404 empty] | 0 | 0
45 | Deploy | Engage & Manage Sponsors | Support and engage sponsors and leaders. | [404 empty] | 0 | 0
46 | Deploy | Mitigate Resistance to Change | Deploy the resistance management plan. | [404 empty] | 0 | 0
47 | Deploy | Mitigate Resistance to Change | Conduct ongoing meetings to track resistance mitigation & identify new resistance. | [404 empty] | 0 | 0
48 | Deploy | Deliver & Track Training | Deliver the training program. | [404 empty] | 0 | 0
49 | Deploy | Deliver & Track Training | Survey trainees to measure the effectiveness and success of the training program. | [404 empty] | 0 | 0
50 | Deploy | Deliver & Track Training | Follow-up with trained employees, and provide additional training as needed. | [404 empty] | 0 | 0
51 | Deploy | Deliver Coaching | Schedule coaching sessions with those being coached. | [404 empty] | 0 | 0
52 | Deploy | Deliver Coaching | Deploy Coaching Plan with the individuals being coached. | [404 empty] | 0 | 0
53 | Deploy | Deliver Coaching | Track coaching success and add more sessions if needed. | [404 empty] | 0 | 0
54 | Deploy | Track Pre-Go-Live Adoption KPIs | Survey impacted groups for adoption metrics before the project goes live. | [404 empty] | 0 | 0
55 | Normalize | Assess & Track Change Risk | Review & begin checking off Stage 3 project deliverables. | [265 empty] | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A
56 | Normalize | Normalize New Behaviors | Deploy support & help resources.
57 | Normalize | Normalize New Behaviors | Send out post go-live communications to communicate where to find support resources, project successes, and lessons learned.
58 | Normalize | Follow-up with Users | Survey impacted groups for adoption metrics after the project goes live.
59 | Normalize | Track Adoption Success | Track and address adoption roadblocks.
60 | Normalize | Address New Resistance | Watch for and address any new post-go-live resistance.
61 | Normalize | Reward Change Network | Celebrate successes, thank and reward the Change Champions Network members.
62 | Exit | Assess & Track Change Risk | Continue checking off Stage 3 project deliverables
63 | Exit | Create OCM Exit Plan | Develop a Change Management Transition/Exit Plan
64 | Exit | Transition OCM | Implement the OCM Exit Plan.
65 | Exit | Final Change Project Reports | Draft the final OCM Project Report, including successes & lessons learned.
66 | Exit | Final Change Project Reports | Socialize the draft of the final OCM Project Report with Project Sponsors & the Project Manager and incorporate their input.
67 | Exit | Final Change Project Reports | Finalize, add any additional reports, and disseminate the final OCM Project Report to the relevant parties.
Insert Duplicate Rows
Airiodion Group Consulting
We can help you increase your change management success Contact Us